# JoyWatch — Team Plan

Two people, four weeks, one working web app.

- Partner A has coding experience. Replace “Partner A” with your name.

- Partner B is new to coding. Replace “Partner B” with her name.

The owner of each page is also written at the top of that page’s PHP file (OWNER:).

## 1. Who does what

The split is built so that Partner B owns real, gradable parts of the project (UI, data, stats, forms, the write-up). Each task copies a pattern that already works somewhere in the starter code. Partner A owns the trickier logic and reviews everything.

### Partner A (experienced): foundation, recommendations, deployment

| Task | Files | Target |
| --- | --- | --- |
| Keymaker setup: upload, import SQL, setup-check.php all ✅ | – | Oct 2 |
| Walk Partner B through the starter code (Friday meeting) | – | Oct 2 |
| Recommendation functions: genre scores, scoring, reasons, confidence | includes/recommend.php | Oct 13 |
| Discover page | discover.php | Oct 14 |
| Tonight results + Random pick | tonight.php | Oct 16 |
| Taste Trainer | trainer.php | Oct 18 |
| Code review of Partner B’s pages (explain each change) | – | weekly |
| Final zip, DEBUG off, submission | – | Oct 22 |
| Stretch: TMDb posters/search, Add a list, bulk edit | includes/tmdb.php, add-list.php, library.php | if time |

### Partner B (new to coding): pages, data, UI, write-up

| Task | Files | Pattern to copy | Target |
| --- | --- | --- | --- |
| Grow the movie catalog in Google Sheets (add favorites, check genres) | database/titles.csv | the existing rows | Oct 6 |
| Library: search box, Movie/TV filter, Sort | library.php (TODO 1–3) | the “view” filter right above them | Oct 8 |
| Save the genre preferences form (pair with A) | taste.php (TODO 1) | title.php saving | Oct 9 |
| About page first draft | about.php | outline is there | Oct 9 |
| Taste “At a glance” numbers | taste.php (TODO 2) | index.php stats query | Oct 13 |
| Settings: save profile + clear data | settings.php | register.php | Oct 15 |
| Export CSV | export.php | step-by-step comments in the file | Oct 16 |
| Taste “Your genres” table with bars | taste.php (TODO 3) | SQL is given in recommend.php | Oct 18 |
| Colors and fonts from Figma → CSS variables | css/style.css (section 1) | – | Oct 18 |
| Test checklist on phone and desktop, screenshots for About | docs/TEST_CHECKLIST.md | – | Oct 21 |
| About page final | about.php | – | Oct 21 |

Both of us: we must each be able to explain every file. The professor may ask either of us about any part.

## 2. Calendar

Today is Sat Sep 26. Classes are Tue/Thu. Office hours are Mon 4–5 and Thu 3–4. Team meetings are Fridays at 4.

| Week | Dates | Goal | Friday 4:00 meeting |
| --- | --- | --- | --- |
| 0: Set up | Sep 26 – Oct 2 | Email the teacher summary. Learn Keymaker in class. Starter running on Keymaker. B does the learning path (section 4). | Oct 2: A walks through the starter (30 min). B makes a first change live (edit the home page text). Confirm Keymaker answers. Assign week 1. |
| 1: MVP | Oct 3 – Oct 9 | Library filters, Taste form save, About draft, bigger catalog | Oct 9: Demo the MVP on Keymaker. Pair-program anything stuck. Assign week 2. |
| 2: Smart features | Oct 10 – Oct 16 | recommend.php, Discover, Tonight, Settings, Export, Taste stats | Oct 16: Feature freeze for core features. Everything is on Keymaker. Pick stretch goals. |
| 3: Polish and submit | Oct 17 – Oct 23 | Trainer, genre bars, Figma styling, testing, About final | Submit Thu Oct 22 night (a day of buffer). Fri Oct 23 at 4: final check on Keymaker. Hard deadline is 11:59 PM. |

Optional second weekly meeting: a short Tuesday or Wednesday check-in (30 min, can be online) to unblock things mid-week. The professor’s online interactive time on Tuesday 7–8 PM is also a good place to ask questions, and it counts toward participation.

### Friday meeting agenda (copy into Drive each week)

- Demo: each person shows what works on Keymaker (10 min)

- Blockers: what’s stuck? Fix it together or pair-program (20 min)

- Teach-back: one concept, explained by whoever built it (10 min)

- Next week: pick tasks from the tables above and update the tracker (10 min)

- Log any AI help used this week in the AI & resources log (2 min)

## 3. How we share work (Google Drive + Keymaker)

### Google Drive folder

JoyWatch – Project 1/
  01 Planning/            PROJECT_PLAN, TEAM_PLAN, Teacher summary (as Google Docs)
  02 Meeting notes/       one Doc per Friday (use the agenda above)
  03 Catalog data/        "JoyWatch titles" Google Sheet (source of titles.csv)
  04 Testing & screenshots/
  05 Code snapshots/      joywatch-YYYY-MM-DD.zip every Friday (a backup)
  06 Submission/          final zip + the URL we submitted
  AI & resources log      (Doc) what tool/site helped, with what, and how we checked it

The .md files open in Google Drive as plain text. The .docx copies in docs/google-drive/ convert into Google Docs (right-click → Open with → Google Docs).

### Code: avoiding overwriting each other

- One official copy lives on Keymaker (in the account the group will submit from) and in the GitHub repo.

- Each person owns specific files (the tables above). Only edit files you own. If you need to change someone else’s file, ask first.

- Practice copy: if we each have our own Keymaker space, Partner B keeps a personal copy there with its own database, so mistakes never break the team site.

- Partner B sends finished files to Partner A (Drive 05 Code snapshots/ or GitHub Desktop, whichever is easier). Partner A reviews them, explains any changes, and updates the official copy.

- Never upload includes/config.php to Drive or GitHub, because it has the database password. Each copy has its own.

### Suggested tools for Partner B

- VS Code (free editor that colors code and shows mistakes) with the “PHP Intelephense” extension

- An SFTP/file upload method, which we’ll learn in class for Keymaker

- The browser, plus phpMyAdmin to see the database tables

## 4. Learning path for Partner B (about 5–6 hours total, week 0)

Do these in order and skip anything already familiar. 1. HTML forms: W3Schools “HTML Forms” and “HTML Input Types” (30 min) 2. PHP basics: W3Schools PHP Intro → Syntax → Variables → Echo → If…Else → Arrays → Loops → Functions (2 hrs) 3. PHP forms: W3Schools “PHP Form Handling” and “Form Validation” (45 min) 4. SQL: W3Schools SQL SELECT, WHERE, ORDER BY, INSERT, UPDATE, DELETE, COUNT/AVG/SUM, GROUP BY, JOIN (1.5 hrs). Try the queries on our tables in phpMyAdmin. 5. Read our code in this order, with comments turned into questions for Friday: index.php → includes/header.php → register.php → includes/db.php → title.php → library.php

The one pattern to learn. Every page in JoyWatch works like this:

require bootstrap           ← turn the app on
if the form was submitted:  ← is_post()
    read the fields         ← post_param('name')
    check they're valid     ← if (...) $errors[] = '...'
    save to the database    ← db_run('UPDATE ... WHERE user_id = ?', [...])
    redirect with a message ← flash('Saved!'); redirect('page.php')
load data for the page      ← db_all('SELECT ...')
include header
print HTML, with h() around every value
include footer

Using AI while learning: allowed in this course, but it must be listed on the About page. It helps most when you ask it to explain a line of our code. Then try writing the next part yourself.

## 5. Definition of done (for any task)

- ☐ Works on Keymaker, not just on one computer

- ☐ Works when logged in as demo and as a brand new user with an empty Library

- ☐ Looks fine at phone width (Chrome DevTools → phone icon → 390px)

- ☐ Every value printed on the page goes through h(), and every SQL value goes through ? placeholders

- ☐ You can explain what every line does

- ☐ “🚧” TODO message removed from the page